## Data
|  | Start Page | 154
|  | End Page | 652
|  | Total Pages | 498
|  | Completed Pages | 29
|  | Remaining Pages | 469
|  | Percentage Complete | 34.06%
Progress Log
|  | Target | [6 empty] | Actual
| Date | Transcriptions | Morphemes | Glosses | Word Translation | Translation | Complete | Remaining | Transcriptions | Morphemes | Glosses | Word Translation | Translation | Complete | Remaining
| 2019-12-08 | 154 | 154 | 154 | 154 | 154 | 0% | 100% | 154 | 154 | 154 | 154 | 154 | 0 | 100%
| 2019-12-09 | 183 | 183 | 183 | 183 | 183 | 5.823% | 94.18% | 183 | 183 | 183 | 183 | 183 | 5.823% | 94.18%
| 2019-12-10 | 233 | 183 | 183 | 183 | 183 | 7.831% | 92.17% | 267 | 183 | 183 | 183 | 183 | 9.197% | 90.8%
| 2019-12-11 | 283 | 183 | 183 | 183 | 183 | 9.839% | 90.16% | 267 | 183 | 183 | 183 | 183 | 9.197% | 90.8%
| 2019-12-12 | 333 | 183 | 183 | 183 | 183 | 11.85% | 88.15% | 347 | 183 | 183 | 183 | 183 | 12.41% | 87.59%
| 2019-12-13 | 383 | 183 | 183 | 183 | 183 | 13.86% | 86.14% | 347 | 183 | 183 | 183 | 183 | 12.41% | 87.59%
| 2019-12-14 | 433 | 183 | 183 | 183 | 183 | 15.86% | 84.14% | 386 | 183 | 183 | 183 | 183 | 13.98% | 86.02%
| 2019-12-15 | 483 | 183 | 183 | 183 | 183 | 17.87% | 82.13% | 469 | 183 | 183 | 183 | 183 | 17.31% | 82.69%
| 2019-12-16 | 533 | 183 | 183 | 183 | 183 | 19.88% | 80.12% | 629 | 183 | 183 | 183 | 183 | 23.73% | 76.27%
| 2019-12-17 | 583 | 183 | 183 | 183 | 183 | 21.89% | 78.11% | 652 | 189 | 183 | 183 | 183 | 24.9% | 75.1%
| 2019-12-18 | 633 | 183 | 183 | 183 | 183 | 23.9% | 76.1% | 652 | 189 | 183 | 183 | 183 | 24.9% | 75.1%
| 2019-12-19 | 652 | 214 | 183 | 183 | 183 | 25.9% | 74.1% | 652 | 189 | 183 | 183 | 183 | 24.9% | 75.1%
| 2019-12-20 | 652 | 264 | 183 | 183 | 183 | 27.91% | 72.09% | 652 | 189 | 183 | 183 | 183 | 24.9% | 75.1%
Christmas | 2019-12-21 | 652 | 264 | 183 | 183 | 183 | 27.91% | 72.09% | 652 | 189 | 183 | 183 | 183 | 24.9% | 75.1%
| 2019-12-22 | 652 | 264 | 183 | 183 | 183 | 27.91% | 72.09% | 652 | 247 | 183 | 183 | 183 | 27.23% | 72.77%
| 2019-12-23 | 652 | 264 | 183 | 183 | 183 | 27.91% | 72.09% | 652 | 417 | 183 | 183 | 183 | 34.06% | 65.94%
| 2019-12-24 | 652 | 264 | 183 | 183 | 183 | 27.91% | 72.09%
| 2019-12-25 | 652 | 264 | 183 | 183 | 183 | 27.91% | 72.09%
| 2019-12-26 | 652 | 264 | 183 | 183 | 183 | 27.91% | 72.09%
| 2019-12-27 | 652 | 264 | 183 | 183 | 183 | 27.91% | 72.09%
| 2019-12-28 | 652 | 314 | 183 | 183 | 183 | 29.92% | 70.08%
| 2019-12-29 | 652 | 364 | 183 | 183 | 183 | 31.93% | 68.07%
| 2019-12-30 | 652 | 414 | 183 | 183 | 183 | 33.94% | 66.06%
| 2019-12-31 | 652 | 464 | 183 | 183 | 183 | 35.94% | 64.06%
| 2020-01-01 | 652 | 514 | 183 | 183 | 183 | 37.95% | 62.05%
LSA / SSILA | 2020-01-02 | 652 | 514 | 183 | 183 | 183 | 37.95% | 62.05%
| 2020-01-03 | 652 | 514 | 183 | 183 | 183 | 37.95% | 62.05%
| 2020-01-04 | 652 | 514 | 183 | 183 | 183 | 37.95% | 62.05%
| 2020-01-05 | 652 | 514 | 183 | 183 | 183 | 37.95% | 62.05%
| 2020-01-06 | 652 | 564 | 183 | 183 | 183 | 39.96% | 60.04%
| 2020-01-07 | 652 | 614 | 183 | 183 | 183 | 41.97% | 58.03%
| 2020-01-08 | 652 | 652 | 195 | 183 | 183 | 43.98% | 56.02%
| 2020-01-09 | 652 | 652 | 245 | 183 | 183 | 45.98% | 54.02%
| 2020-01-10 | 652 | 652 | 295 | 183 | 183 | 47.99% | 52.01%
| 2020-01-11 | 652 | 652 | 345 | 183 | 183 | 50% | 50%
| 2020-01-12 | 652 | 652 | 395 | 183 | 183 | 52.01% | 47.99%
| 2020-01-13 | 652 | 652 | 445 | 183 | 183 | 54.02% | 45.98%
| 2020-01-14 | 652 | 652 | 495 | 183 | 183 | 56.02% | 43.98%
| 2020-01-15 | 652 | 652 | 545 | 183 | 183 | 58.03% | 41.97%
| 2020-01-16 | 652 | 652 | 595 | 183 | 183 | 60.04% | 39.96%
| 2020-01-17 | 652 | 652 | 645 | 183 | 183 | 62.05% | 37.95%
| 2020-01-18 | 652 | 652 | 652 | 236 | 183 | 64.46% | 35.54%
| 2020-01-19 | 652 | 652 | 652 | 286 | 183 | 66.47% | 33.53%
| 2020-01-20 | 652 | 652 | 652 | 336 | 183 | 68.47% | 31.53%
| 2020-01-21 | 652 | 652 | 652 | 386 | 183 | 70.48% | 29.52%
| 2020-01-22 | 652 | 652 | 652 | 436 | 183 | 72.49% | 27.51%
| 2020-01-23 | 652 | 652 | 652 | 486 | 183 | 74.5% | 25.5%
| 2020-01-24 | 652 | 652 | 652 | 536 | 183 | 76.51% | 23.49%
| 2020-01-25 | 652 | 652 | 652 | 586 | 183 | 78.51% | 21.49%
| 2020-01-26 | 652 | 652 | 652 | 636 | 183 | 80.52% | 19.48%
| 2020-01-27 | 652 | 652 | 652 | 652 | 217 | 82.53% | 17.47%
| 2020-01-28 | 652 | 652 | 652 | 652 | 267 | 84.54% | 15.46%
| 2020-01-29 | 652 | 652 | 652 | 652 | 317 | 86.55% | 13.45%
| 2020-01-30 | 652 | 652 | 652 | 652 | 367 | 88.55% | 11.45%
| 2020-01-31 | 652 | 652 | 652 | 652 | 417 | 90.56% | 9.438%
| 2020-02-01 | 652 | 652 | 652 | 652 | 467 | 92.57% | 7.43%
| 2020-02-02 | 652 | 652 | 652 | 652 | 517 | 94.58% | 5.422%
| 2020-02-03 | 652 | 652 | 652 | 652 | 567 | 96.59% | 3.414%
| 2020-02-04 | 652 | 652 | 652 | 652 | 617 | 98.59% | 1.406%
| 2020-02-05 | 652 | 652 | 652 | 652 | 652 | 100% | 0%